## BACKEND TESTS
No | Req ID | Req Desc | TC ID | TC Desc | Test Design | Test Designer | UAT Test Req? | Test Execution |  |  | Defects? | Defect ID | Defect Status | Req Coverage Status
[8 empty] | Test Env | UAT Env | Prod Env
1 | UC-01 | Register Account | TC-BE-01-001 | Valid name + email + password → users row created with id, name, email, role=reader, coinBalance=0 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
2 |  |  | TC-BE-01-002 | Password stored as bcrypt hash in DB — plaintext never present | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
3 |  |  | TC-BE-01-003 | New user assigned role=reader (not curator or admin) by default | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
4 |  |  | TC-BE-01-004 | New user assigned coinBalance=0; no coin_transactions row created on registration | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
5 |  |  | TC-BE-01-005 | Authenticated session created immediately; session cookie set httpOnly=true | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
6 |  |  | TC-BE-01-006 | Session cookie has Secure=true and SameSite=Lax attributes | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
7 |  |  | TC-BE-01-007 | Empty display name (BR-01-1) → 400; no user created | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
8 |  |  | TC-BE-01-008 | Name = 101 chars (BR-01-1 max=100) → 400; name = 100 chars → accepted | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
9 |  |  | TC-BE-01-009 | Name with leading/trailing whitespace → 400 (BR-01-1 printable, no surrounding whitespace) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
10 |  |  | TC-BE-01-010 | Invalid email format "notanemail" (BR-01-2) → 400; no user created | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
11 |  |  | TC-BE-01-011 | Email stored lowercase; submission "User@Example.COM" → stored as "user@example.com" | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
12 |  |  | TC-BE-01-012 | Password = 7 chars (BR-01-3 min=8) → 400; no user created | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
13 |  |  | TC-BE-01-013 | Password = 8 chars (BR-01-3 boundary) → accepted | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
14 |  |  | TC-BE-01-014 | Password = 128 chars (no maximum) → accepted | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
15 |  |  | TC-BE-01-015 | Duplicate email (exact match, BR-01-4) → 409; second user not created | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
16 |  |  | TC-BE-01-016 | Duplicate email case-insensitive (BR-01-4): "user@x.com" vs "USER@X.COM" → same account | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
17 |  |  | TC-BE-01-017 | callbackUrl = same origin "/library" (BR-01-7) → redirect honoured after registration | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
18 |  |  | TC-BE-01-018 | callbackUrl = external "https://evil.com" (BR-01-7) → rejected; redirect to / | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
19 |  |  | TC-BE-01-019 | Concurrent registration with same email → exactly one user row; second returns 409 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
20 |  |  | TC-BE-01-020 | Missing required field (email omitted) → 400 with field-level error | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
21 | UC-02 | Sign In with Email | TC-BE-02-001 | Correct email + password → session row created in sessions table | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
22 |  |  | TC-BE-02-002 | Correct credentials → httpOnly, Secure, SameSite=Lax session cookie set | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
23 |  |  | TC-BE-02-003 | Wrong password → generic MSG-002 returned; response body does not reveal if email exists | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
24 |  |  | TC-BE-02-004 | Non-existent email → exact same error body as wrong-password (no enumeration, BR-02-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
25 |  |  | TC-BE-02-005 | 1st–9th consecutive failed attempts: each blocked, counter increments | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
26 |  |  | TC-BE-02-006 | 10th failed attempt in 15-min window → IP rate-limited; 429 returned (BR-02-3) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
27 |  |  | TC-BE-02-007 | After rate-limit: correct credentials still blocked until 15-min window expires | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
28 |  |  | TC-BE-02-008 | Rate-limit counter resets after 15 min (new window allows login again) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
29 |  |  | TC-BE-02-009 | rememberMe=true → session TTL=2592000 s (30 days, BR-02-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
30 |  |  | TC-BE-02-010 | rememberMe=false (default) → session TTL=86400 s (1 day) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
31 |  |  | TC-BE-02-011 | Same-origin callbackUrl=/library honored after sign-in (BR-02-4) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
32 |  |  | TC-BE-02-012 | External callbackUrl rejected; redirected to / (BR-02-4) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
33 |  |  | TC-BE-02-013 | Google-only account email submitted to email sign-in → appropriate error returned | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
34 |  |  | TC-BE-02-014 | Email comparison case-insensitive (stored lowercase, submitted uppercase → matches) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
35 | UC-03 | Sign In with Google | TC-BE-03-001 | Completely new Google identity → users row created: role=reader, coinBalance=0 | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Partial
36 |  |  | TC-BE-03-002 | New Google user → display name sourced from Google profile (BR-03-3) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
37 |  |  | TC-BE-03-003 | New Google user → passwordHash is null in users table (BR-03-4) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
38 |  |  | TC-BE-03-004 | Google email matches existing email/password account → accounts row linked; no new user (BR-03-1) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
39 |  |  | TC-BE-03-005 | Linked account: subsequent sign-in with same Google subject returns existing user (BR-03-2) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
40 |  |  | TC-BE-03-006 | Same Google subject revisited → no duplicate users row created (BR-03-2) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
41 |  |  | TC-BE-03-007 | OAuth state parameter (CSRF nonce) mismatch → request rejected, no user created | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
42 |  |  | TC-BE-03-008 | OAuth code exchange fails (Google error) → redirect to /sign-in, no user (BR-03-5) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
43 |  |  | TC-BE-03-009 | User cancels Google consent → redirect to /sign-in, no user (BR-03-5) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
44 |  |  | TC-BE-03-010 | Google access/refresh tokens NOT stored in any DB table (BR-03-4) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
45 | UC-04 | Sign Out | TC-BE-04-001 | Sign-out POST → session row deleted from sessions table (BR-04-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
46 |  |  | TC-BE-04-002 | Response header sets session cookie Max-Age=0 (BR-04-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
47 |  |  | TC-BE-04-003 | Old session token reused after sign-out → 401 Unauthorized | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
48 |  |  | TC-BE-04-004 | Sign-out redirects to / (BR-04-3); never to a protected page | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
49 |  |  | TC-BE-04-005 | Unauthenticated POST to sign-out → handled gracefully (200 or 401, no 500) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
50 |  |  | TC-BE-04-006 | All other sessions for the same user remain valid after single sign-out | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
51 | UC-05 | Reset Password | TC-BE-05-001 | Known email → token generated and reset email sent (BR-05-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
52 |  |  | TC-BE-05-002 | Unknown email → neutral MSG-024 shown; no verifications row created (BR-05-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
53 |  |  | TC-BE-05-003 | Response body identical whether email found or not (no enumeration, BR-05-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
54 |  |  | TC-BE-05-004 | Reset token stored as SHA-256 hash; raw token never in DB (BR-05-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
55 |  |  | TC-BE-05-005 | Token expires after 3600 s: use after expiry → 400/410 (BR-05-3) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
56 |  |  | TC-BE-05-006 | Token at exactly 3599 s → accepted; at 3601 s → rejected (boundary) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
57 |  |  | TC-BE-05-007 | Token single-use: successful reset then reuse same token → rejected (BR-05-4) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
58 |  |  | TC-BE-05-008 | New password = 7 chars → rejected 400 (BR-05-5) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
59 |  |  | TC-BE-05-009 | New password = 8 chars (boundary) → accepted | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
60 |  |  | TC-BE-05-010 | New password same as current → rejected with MSG-017 (BR-05-5) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
61 |  |  | TC-BE-05-011 | Successful reset → all other sessions for that user invalidated (BR-05-4) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
62 |  |  | TC-BE-05-012 | Successful reset → redirect to /sign-in with MSG-004 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
63 |  |  | TC-BE-05-013 | Google-only account POST to reset-password endpoint → error (BR-05-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
64 |  |  | TC-BE-05-014 | Second reset request for same email → old token invalidated; new token sent | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
65 | UC-06 | Browse Novel List | TC-BE-06-001 | Default response: published novels sorted by updatedAt DESC (BR-06-1) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
66 |  |  | TC-BE-06-002 | page=1 returns first 30 novels; page=2 returns next 30 (BR-06-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
67 |  |  | TC-BE-06-003 | page beyond total pages → empty array returned (no 500) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
68 |  |  | TC-BE-06-004 | status=COMPLETED → only COMPLETED novels in results (BR-06-4) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
69 |  |  | TC-BE-06-005 | status=ONGOING → only ONGOING novels | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
70 |  |  | TC-BE-06-006 | status=HIATUS → only HIATUS novels | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
71 |  |  | TC-BE-06-007 | status=DROPPED → only DROPPED novels | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
72 |  |  | TC-BE-06-008 | Unknown status value → falls back to no filter; all published novels returned (BR-06-4) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
73 |  |  | TC-BE-06-009 | genre=<id> → only novels with that genre in results (BR-06-5) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
74 |  |  | TC-BE-06-010 | Multiple genre params → only first applied (BR-06-5) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
75 |  |  | TC-BE-06-011 | sort=trending → ordered by totalViews DESC (BR-06-2) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
76 |  |  | TC-BE-06-012 | sort=rating → ordered by avgRating DESC | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
77 |  |  | TC-BE-06-013 | sort=chapters → ordered by totalChapters DESC | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
78 |  |  | TC-BE-06-014 | sort=unknown → falls back to updatedAt; no 400 (BR-06-2) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
79 |  |  | TC-BE-06-015 | Combined status=COMPLETED + genre → AND-filtered results | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
80 |  |  | TC-BE-06-016 | Zero-match filter combination → empty array + result count 0 (BR-06-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
81 |  |  | TC-BE-06-017 | DRAFT novels never appear in public browse results | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
82 |  |  | TC-BE-06-018 | page=0 → treated as page=1; first 30 results returned (no 400) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
83 |  |  | TC-BE-06-019 | page=-1 or page=NaN → defaults to page=1; no 500 error | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
84 |  |  | TC-BE-06-020 | limit query param ignored; server enforces fixed page size of 30 (BR-06-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
85 |  |  | TC-BE-06-021 | sort=rating: novels with avgRating=null sorted after rated novels (nulls last) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
86 |  |  | TC-BE-06-022 | Triple combination: status + genre + sort → results satisfy all three constraints | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
87 | UC-07 | Search Novels | TC-BE-07-001 | Meilisearch exact-title query returns correct novel in < 500 ms P95 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
88 |  |  | TC-BE-07-002 | Empty query string → Meilisearch not called; full novel list returned (BR-07-1) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
89 |  |  | TC-BE-07-003 | Query with 1-char typo returns matching novel (BR-07-4 typo tolerance) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
90 |  |  | TC-BE-07-004 | Search scope: matches title and synopsis; genre/tag names not indexed (BR-07-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
91 |  |  | TC-BE-07-005 | Meilisearch slow (> 400 ms) → DB ILIKE fallback triggered (BR-07-5) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
92 |  |  | TC-BE-07-006 | Meilisearch throws error → DB ILIKE fallback executes | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
93 |  |  | TC-BE-07-007 | DB fallback returns results within 1 s | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
94 |  |  | TC-BE-07-008 | Both Meilisearch and DB fail → empty array returned; no exception thrown | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
95 |  |  | TC-BE-07-009 | MEILISEARCH_API_KEY not present in any response body or header | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
96 |  |  | TC-BE-07-010 | Search + status=COMPLETED → AND-filtered (BR-07-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
97 |  |  | TC-BE-07-011 | Search + genre filter → AND-filtered in same Meilisearch request | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
98 |  |  | TC-BE-07-012 | Vietnamese diacritics: "thánh nhân" query matches "Thánh Nhân Lộ" correctly | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
99 |  |  | TC-BE-07-013 | Special chars in query (quotes, slashes) do not cause 500 or injection | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
100 |  |  | TC-BE-07-014 | Meilisearch index updated within 60 s of chapter PUBLISHED status change | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
101 |  |  | TC-BE-07-015 | Single-char query returns results; no minimum query-length enforced | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
102 |  |  | TC-BE-07-016 | 200-char query handled gracefully; no 500 or timeout | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
103 |  |  | TC-BE-07-017 | 10 concurrent search requests → all return 200; no race conditions or contention | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
104 |  |  | TC-BE-07-018 | Case-insensitive matching: "THIEN DAO" query matches novel with Vietnamese title | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
105 | UC-08 | Filter Novels | TC-BE-08-001 | status + genre filter AND-combined in single DB/search query (BR-08-5) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
106 |  |  | TC-BE-08-002 | Toggling active status filter removes param; full list restored (BR-08-1) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
107 |  |  | TC-BE-08-003 | Toggling active genre filter removes param (BR-08-2) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
108 |  |  | TC-BE-08-004 | URL ?status=COMPLETED&genre=X on reload → identical view restored (BR-08-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
109 |  |  | TC-BE-08-005 | Genre options sourced from DB genres table; no hardcoded list | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
110 |  |  | TC-BE-08-006 | Unknown genre ID returns empty result, not 500 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
111 |  |  | TC-BE-08-007 | Result count reflects filter combination accurately (BR-08-4) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
112 |  |  | TC-BE-08-008 | Filter + pagination: ?status=COMPLETED&page=2 → correct page within filtered subset | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
113 |  |  | TC-BE-08-009 | Genre ID with SQL injection attempt → safe; 400 or empty result; no 500 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
114 |  |  | TC-BE-08-010 | ?status=completed (lowercase) → treated same as COMPLETED or ignored; no 500 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
115 |  |  | TC-BE-08-011 | Multiple ?status= params → first value used; subsequent values silently ignored | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
116 |  |  | TC-BE-08-012 | All active filters cleared simultaneously → full novel list restored without reload | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
117 | UC-09 | View Novel Detail | TC-BE-09-001 | Valid slug → 200 with full novel data | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
118 |  |  | TC-BE-09-002 | Non-existent slug → 404 (BR-09-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
119 |  |  | TC-BE-09-003 | DRAFT chapters excluded from public chapter list (BR-09-3) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
120 |  |  | TC-BE-09-004 | Future-scheduled chapters (publishedAt > now) excluded | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
121 |  |  | TC-BE-09-005 | Response <head> includes og:title matching novel title | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
122 |  |  | TC-BE-09-006 | Response <head> includes og:description | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
123 |  |  | TC-BE-09-007 | Response <head> includes canonical URL for the novel detail page | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
124 |  |  | TC-BE-09-008 | totalViews incremented fire-and-forget; page load not blocked (BR-09-2) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
125 |  |  | TC-BE-09-009 | Authenticated reader: reading_progress fetched; "Tiếp tục đọc" CTA populated | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
126 |  |  | TC-BE-09-010 | No reading progress → "Đọc từ đầu" CTA (first chapter link) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
127 |  |  | TC-BE-09-011 | No published chapters → "Chưa có chương" disabled CTA | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
128 |  |  | TC-BE-09-012 | Novel with no reviews → avgRating not displayed (BR-09-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
129 |  |  | TC-BE-09-013 | Recommendations: ≤6 same-genre novels, current novel excluded (BR-09-5) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
130 |  |  | TC-BE-09-014 | VIP chapters show isVip=true flag in chapter list (BR-09-4) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
131 |  |  | TC-BE-09-015 | Cover image URL is Cloudinary CDN domain | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
132 |  |  | TC-BE-09-016 | Redis cache hit: second request for same novel slug served from cache in < 10 ms | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
133 |  |  | TC-BE-09-017 | Cache invalidated on novel update; subsequent request hits DB and refreshes cache | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
134 |  |  | TC-BE-09-018 | og:image meta tag set to coverUrl when cover is present; absent otherwise | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
135 |  |  | TC-BE-09-019 | Novel with 0 published chapters: chapter list is empty array; no error thrown | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
136 |  |  | TC-BE-09-020 | totalChapters field matches exact count of PUBLISHED chapters in DB | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
137 | UC-10 | Read Chapter | TC-BE-10-001 | Free chapter: full content in server HTML response for unauthenticated guest | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
138 |  |  | TC-BE-10-002 | Free chapter: no authentication required (BR-10-3 guest allowed) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
139 |  |  | TC-BE-10-003 | Free chapter Cache-Control: s-maxage=60, stale-while-revalidate=3600 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
140 |  |  | TC-BE-10-004 | VIP chapter: content=null in server response for unauthenticated guest (BR-10-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
141 |  |  | TC-BE-10-005 | VIP chapter: content NOT hidden via CSS — completely absent from HTML (BR-10-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
142 |  |  | TC-BE-10-006 | VIP chapter: content=null for authenticated reader with 0 coins and no subscription | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
143 |  |  | TC-BE-10-007 | VIP chapter: full content returned after reader completes coin unlock (BR-10-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
144 |  |  | TC-BE-10-008 | VIP chapter: full content returned for reader with active subscription (BR-10-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
145 |  |  | TC-BE-10-009 | VIP access check queries chapter_unlocks table in DB — not Redis (BR-10-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
146 |  |  | TC-BE-10-010 | VIP access check queries subscriptions table in DB — not Redis | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
147 |  |  | TC-BE-10-011 | checkAccess() called before chapter content DB query (access-first ordering, BR-10-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
148 |  |  | TC-BE-10-012 | Non-existent chapter number → 404 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
149 |  |  | TC-BE-10-013 | DRAFT chapter → 404 for public access (not visible to readers) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
150 |  |  | TC-BE-10-014 | Future-scheduled chapter (publishedAt > now) → 404 or 403 for readers | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
151 |  |  | TC-BE-10-015 | Prev chapter link correct (BR-10-6): chapter 3 prev = chapter 2 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
152 |  |  | TC-BE-10-016 | Next chapter link absent for last chapter (BR-10-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
153 |  |  | TC-BE-10-017 | Reading time estimate = ceil(wordCount / 250) minutes (BR-10-5) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
154 |  |  | TC-BE-10-018 | Authenticated: reading_progress upserted after chapter load (BR-10-4) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
155 |  |  | TC-BE-10-019 | Re-reading earlier chapter: progress NOT overwritten (forward-only, BR-10-4) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
156 |  |  | TC-BE-10-020 | Chapter content page JS payload < 50 KB (RSC — no client hydration) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
157 |  |  | TC-BE-10-021 | incrementChapterViews fires without blocking response (fire-and-forget) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
158 | UC-11 | Adjust Reader Settings | TC-BE-11-001 | Default settings: theme=dark, font=serif, fontSize=18, lineHeight=1.85, width=680 (BR-11-1) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Partial
159 |  |  | TC-BE-11-002 | Settings stored in localStorage key "reader-settings" as JSON (BR-11-2) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
160 |  |  | TC-BE-11-003 | No API call or DB write on settings change (BR-11-4) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
161 |  |  | TC-BE-11-004 | Theme change applies to .chapter-content only; site header unaffected (BR-11-3) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
162 |  |  | TC-BE-11-005 | Dark theme class applied before first paint via inline script (no flash) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
163 |  |  | TC-BE-11-006 | fontSize slider range 14–26 px; values outside range rejected by UI | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
164 |  |  | TC-BE-11-007 | lineHeight slider range 1.4–2.2; step 0.1 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
165 |  |  | TC-BE-11-008 | contentWidth slider range 480–900 px; step 10 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
166 |  |  | TC-BE-11-009 | Corrupted JSON in localStorage "reader-settings" → defaults applied; no runtime error | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
167 |  |  | TC-BE-11-010 | localStorage key absent (first visit) → all defaults applied without throwing | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
168 |  |  | TC-BE-11-011 | Settings are scoped to browser localStorage; clearing localStorage resets to defaults | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
169 | UC-12 | Follow Novel | TC-BE-12-001 | Follow: novel_follows row inserted for (userId, novelId) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
170 |  |  | TC-BE-12-002 | Follow without session → 401 (BR-12-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
171 |  |  | TC-BE-12-003 | Duplicate follow (INSERT ON CONFLICT DO NOTHING, BR-12-2) → 200, no duplicate row | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
172 |  |  | TC-BE-12-004 | Unfollow: novel_follows row deleted | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
173 |  |  | TC-BE-12-005 | Double unfollow → no error; idempotent (BR-12-2) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
174 |  |  | TC-BE-12-006 | Follow non-existent novel → 404 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
175 |  |  | TC-BE-12-007 | Follow state drives notification fan-out on chapter publish (BR-12-3) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
176 |  |  | TC-BE-12-008 | Follow count accurately reflects novel_follows rows for that novel | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
177 | UC-13 | Track Reading Progress | TC-BE-13-001 | First visit to a chapter → reading_progress row inserted (BR-13-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
178 |  |  | TC-BE-13-002 | Second visit to same chapter → only one row exists (composite PK, BR-13-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
179 |  |  | TC-BE-13-003 | Re-reading earlier chapter → progress row NOT downgraded (forward-only, BR-13-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
180 |  |  | TC-BE-13-004 | Reading higher chapter number → progress row updated to new chapter (BR-13-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
181 |  |  | TC-BE-13-005 | Unauthenticated read → no reading_progress write (BR-13-4) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
182 |  |  | TC-BE-13-006 | Progress save does not block chapter page render (fire-and-forget) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
183 |  |  | TC-BE-13-007 | Progress percentage = ceil(lastChapterNumber / totalChapters * 100), max 100 (BR-13-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
184 |  |  | TC-BE-13-008 | Novel detail "Tiếp tục đọc" CTA uses stored lastChapterNumber | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
185 | UC-14 | View Library | TC-BE-14-001 | /library → 401/redirect for unauthenticated guest (BR-14-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
186 |  |  | TC-BE-14-002 | Library lists novel_follows joined with novels for authenticated user | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
187 |  |  | TC-BE-14-003 | "Đang đọc" tab: novels where lastChapterNumber < totalChapters | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
188 |  |  | TC-BE-14-004 | "Hoàn thành" tab: novels where lastChapterNumber >= totalChapters | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
189 |  |  | TC-BE-14-005 | "Tất cả" tab: all followed novels regardless of progress (BR-14-4 default) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
190 |  |  | TC-BE-14-006 | No followed novels → empty state with link to /novels (BR-14-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
191 |  |  | TC-BE-14-007 | Progress bar value = lastChapterNumber / totalChapters (BR-14-2) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
192 |  |  | TC-BE-14-008 | Library data is DB-backed — localStorage clear does not affect it | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
193 | UC-15 | Write Review | TC-BE-15-001 | Review create → 401 for unauthenticated user (BR-15-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
194 |  |  | TC-BE-15-002 | First review: reviews row inserted with userId, novelId, rating, body | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
195 |  |  | TC-BE-15-003 | Second review same user+novel → upserts (updates) existing row — no duplicate (BR-15-2) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
196 |  |  | TC-BE-15-004 | Rating = 0 → 400 rejected (BR-15-3 min=1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
197 |  |  | TC-BE-15-005 | Rating = 6 → 400 rejected (BR-15-3 max=5) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
198 |  |  | TC-BE-15-006 | Rating = 1 and = 5 (boundaries) → accepted | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
199 |  |  | TC-BE-15-007 | Body omitted (null/empty) → accepted (BR-15-4 optional) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
200 |  |  | TC-BE-15-008 | Body = 2001 chars → 400; body = 2000 chars → accepted (BR-15-4) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
201 |  |  | TC-BE-15-009 | avgRating on novels row recalculated after review upsert (BR-15-5) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
202 |  |  | TC-BE-15-010 | Review delete: own review deleted; avgRating recalculated (BR-15-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
203 |  |  | TC-BE-15-011 | Review delete: attempting to delete another user's review → 403 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
204 |  |  | TC-BE-15-012 | Review vote: duplicate vote (same userId+reviewId) → no-op, no error | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
205 |  |  | TC-BE-15-013 | Review list for novel paginated at 20 per page (BR-15-7 if defined) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
206 |  |  | TC-BE-15-014 | Review upvote: review_votes row inserted; voteCount on review increments | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
207 |  |  | TC-BE-15-015 | Review vote on own review → rejected with 403 (BR-15-8) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
208 |  |  | TC-BE-15-016 | Review body with XSS attempt: <script>alert(1)</script> stripped; plain text stored | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
209 |  |  | TC-BE-15-017 | Review update by author: new rating and body replace old values in DB | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
210 | UC-16 | Leave Comment | TC-BE-16-001 | Comment create → 401 for unauthenticated user (BR-16-1) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
211 |  |  | TC-BE-16-002 | Valid comment → comments row with userId, targetType, targetId, content, parentId=null | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
212 |  |  | TC-BE-16-003 | Empty comment body → 400 (BR-16-2 non-empty) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
213 |  |  | TC-BE-16-004 | Comment = 1001 chars → 400; = 1000 chars → accepted (BR-16-2 max) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
214 |  |  | TC-BE-16-005 | Reply with valid parentId (parent.parentId===null) → accepted (BR-16-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
215 |  |  | TC-BE-16-006 | Reply to a reply (parent.parentId !== null) → 400 depth guard (BR-16-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
216 |  |  | TC-BE-16-007 | Invalid (non-existent) parentId → 400 (BR-16-3) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
217 |  |  | TC-BE-16-008 | Comment within 15 min: edit allowed for owner (BR-16-4) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
218 |  |  | TC-BE-16-009 | Comment after 15 min: edit rejected for reader; admin still allowed (BR-16-4) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
219 |  |  | TC-BE-16-010 | Hidden comment (isHidden=true) not returned by public findAll (BR-16-5) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
220 |  |  | TC-BE-16-011 | Top-level comments sorted by createdAt DESC (newest first, BR-16-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
221 |  |  | TC-BE-16-012 | Replies sorted by createdAt ASC (oldest first, BR-16-6) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
222 |  |  | TC-BE-16-013 | Comment vote: duplicate vote (same userId+commentId) → no-op (idempotent) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
223 |  |  | TC-BE-16-014 | Admin hides comment: isHidden=true in DB; hidden comment absent from public response | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
224 |  |  | TC-BE-16-015 | Report comment: reports row created with targetType=comment, targetId=commentId | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
225 |  |  | TC-BE-16-016 | Comment body with XSS: <script> tag stripped before DB write | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
226 |  |  | TC-BE-16-017 | Comment list paginated at 20 per page; page 2 returns next 20 comments | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
227 |  |  | TC-BE-16-018 | targetType=novel vs targetType=chapter correctly stored per request context | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
228 | UC-17 | Purchase Coins via MoMo | TC-BE-17-001 | payments row with status=PENDING, orderId, userId, amountVnd created before redirect (step 4) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Partial
229 |  |  | TC-BE-17-002 | Each payment initiation produces a unique orderId | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
230 |  |  | TC-BE-17-003 | Unauthenticated user cannot initiate coin purchase → 401 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
231 |  |  | TC-BE-17-004 | Initiation with inactive coin package → 404/400 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
232 |  |  | TC-BE-17-005 | Valid HMAC-SHA256 signature → webhook proceeds | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
233 |  |  | TC-BE-17-006 | Invalid HMAC → 400 returned; no coins credited; no DB write | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
234 |  |  | TC-BE-17-007 | Missing HMAC field entirely → 400 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
235 |  |  | TC-BE-17-008 | Empty string HMAC → 400 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
236 |  |  | TC-BE-17-009 | HMAC comparison must be constant-time (prevent timing attacks) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
237 |  |  | TC-BE-17-010 | resultCode=0 (success): coins credited, status=COMPLETED, coin_transactions created | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
238 |  |  | TC-BE-17-011 | resultCode≠0 (failure): payments.status=FAILED; users.coinBalance unchanged | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
239 |  |  | TC-BE-17-012 | resultCode≠0: no coin_transactions row written | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
240 |  |  | TC-BE-17-013 | coinBalance increment + coin_transactions insert in single DB transaction (BR atomic) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
241 |  |  | TC-BE-17-014 | Transaction partial failure rolls back both coinBalance and coin_transactions | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
242 |  |  | TC-BE-17-015 | orderId already SUCCESS: second webhook → 200; coinBalance unchanged (idempotency) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
243 |  |  | TC-BE-17-016 | orderId already SUCCESS: no second coin_transactions row inserted | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
244 |  |  | TC-BE-17-017 | orderId already FAILED: second webhook with resultCode=0 → re-process or reject safely | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
245 |  |  | TC-BE-17-018 | Concurrent webhooks for same orderId → exactly one credit (race guard) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
246 |  |  | TC-BE-17-019 | Coin amount matches totalCoins from coin_packages (base + bonus) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
247 |  |  | TC-BE-17-020 | Webhook handler completes within 10 s (Vercel Hobby plan limit) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
248 |  |  | TC-BE-17-021 | MOMO_SECRET_KEY not present in any browser-accessible response | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
249 |  |  | TC-BE-17-022 | orderId not found in payments → return 200 to MoMo (no retry storm); no credit | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
250 | UC-18 | Unlock VIP Chapter | TC-BE-18-001 | Unlock without session → 401 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
251 |  |  | TC-BE-18-002 | Unlock non-VIP chapter → 400 (cannot unlock free chapter) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
252 |  |  | TC-BE-18-003 | Non-existent chapter → 404 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
253 |  |  | TC-BE-18-004 | Successful unlock: users.coinBalance decremented by 1 | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
254 |  |  | TC-BE-18-005 | Successful unlock: chapter_unlocks row (userId, chapterId) created | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
255 |  |  | TC-BE-18-006 | Successful unlock: coin_transactions row with type=DEBIT, amount=1 | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
256 |  |  | TC-BE-18-007 | All three writes in single DB transaction (atomic, BR coin integrity) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
257 |  |  | TC-BE-18-008 | Transaction rollback test: simulated failure after coinBalance decrement → no partial state | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
258 |  |  | TC-BE-18-009 | coinBalance = 0 → 402 insufficient_coins; no debit, no unlock row | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
259 |  |  | TC-BE-18-010 | coinBalance = 1 → unlock succeeds; coinBalance becomes 0 | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
260 |  |  | TC-BE-18-011 | coinBalance never goes below 0 in any scenario | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
261 |  |  | TC-BE-18-012 | Already-unlocked chapter → 200 idempotent; no second debit (BR check existing unlock) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
262 |  |  | TC-BE-18-013 | Already-unlocked chapter → no second coin_transactions row | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
263 |  |  | TC-BE-18-014 | chapter_unlocks UNIQUE (userId, chapterId) DB constraint prevents duplicate unlock | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
264 |  |  | TC-BE-18-015 | Concurrent unlock requests from same user → exactly one debit (SELECT FOR UPDATE) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
265 |  |  | TC-BE-18-016 | Two concurrent requests at coinBalance=1 → one succeeds (200), one gets 402 | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
266 |  |  | TC-BE-18-017 | coinBalance never read from Redis or any cache — always from DB in transaction | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
267 |  |  | TC-BE-18-018 | coin_transactions ledger sum equals users.coinBalance after every operation | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
268 |  |  | TC-BE-18-019 | Active subscription: VIP chapter accessible without spending coins (no chapter_unlocks needed) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
269 |  |  | TC-BE-18-020 | Unlock persists after session expiry — chapter_unlocks checked on next visit | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
270 | UC-19 | Update Profile | TC-BE-19-001 | Profile update → 401 for unauthenticated | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
271 |  |  | TC-BE-19-002 | Valid name update → users.name updated in DB | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
272 |  |  | TC-BE-19-003 | Name = empty string → rejected | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
273 |  |  | TC-BE-19-004 | Name > 100 chars → rejected | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
274 |  |  | TC-BE-19-005 | hasPassword() returns false for Google-only account (BR-03-4) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
275 |  |  | TC-BE-19-006 | Change-password form hidden server-side for Google-only accounts | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
276 |  |  | TC-BE-19-007 | Email field is immutable; email update attempt → rejected or silently ignored | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
277 |  |  | TC-BE-19-008 | Updated name reflects in navbar on next page load | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
278 | UC-20 | Change Password | TC-BE-20-001 | Change password → 401 for unauthenticated | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
279 |  |  | TC-BE-20-002 | Wrong current password → 400/403; password not changed | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
280 |  |  | TC-BE-20-003 | Correct current password → update proceeds | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
281 |  |  | TC-BE-20-004 | New password = 7 chars → 400 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
282 |  |  | TC-BE-20-005 | New password = 8 chars → accepted (boundary) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
283 |  |  | TC-BE-20-006 | New password same as current → 400 with MSG-017 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
284 |  |  | TC-BE-20-007 | Successful change → all other sessions invalidated | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
285 |  |  | TC-BE-20-008 | Successful change → current session remains valid | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
286 |  |  | TC-BE-20-009 | Google-only account → change password endpoint returns error | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
287 |  |  | TC-BE-20-010 | New password hash differs from old hash in DB | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
288 | UC-21 | Curator Manage Novel | TC-BE-21-001 | Novel create → 401 for unauthenticated | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
289 |  |  | TC-BE-21-002 | Novel create → 403 for reader role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
290 |  |  | TC-BE-21-003 | Novel create → 200 for curator role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
291 |  |  | TC-BE-21-004 | Novel create → 200 for admin role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
292 |  |  | TC-BE-21-005 | Slug auto-generated from title via slugify (spaces → hyphens, diacritics stripped) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
293 |  |  | TC-BE-21-006 | Duplicate slug → 409 (DB UNIQUE index on novels.slug) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
294 |  |  | TC-BE-21-007 | Empty title → 400 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
295 |  |  | TC-BE-21-008 | Title > 500 chars → 400 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
296 |  |  | TC-BE-21-009 | Valid Cloudinary URL accepted for coverUrl | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
297 |  |  | TC-BE-21-010 | Genre IDs associated atomically (no orphan novel_genres rows on failure) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
298 |  |  | TC-BE-21-011 | Tag IDs associated atomically | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
299 |  |  | TC-BE-21-012 | Novel update by owner curator → 200 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
300 |  |  | TC-BE-21-013 | Novel delete removes all associated chapters, novel_genres, novel_tags | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
301 |  |  | TC-BE-21-014 | Status change to PUBLISHED → novel appears in public browse list | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
302 | UC-22 | Curator Manage Chapter | TC-BE-22-001 | Chapter create → 401 for unauthenticated | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
303 |  |  | TC-BE-22-002 | Chapter create → 403 for reader role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
304 |  |  | TC-BE-22-003 | Chapter create → 200 for curator role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
305 |  |  | TC-BE-22-004 | Chapter content: <script>alert(1)</script> stripped by DOMPurify before DB write | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
306 |  |  | TC-BE-22-005 | Chapter content: onclick attribute stripped (stored XSS prevention) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
307 |  |  | TC-BE-22-006 | Chapter content: <p>, <em>, <strong>, <br> preserved by DOMPurify | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
308 |  |  | TC-BE-22-007 | chapterNumber must be positive integer; 0 → 400; negative → 400 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
309 |  |  | TC-BE-22-008 | Duplicate chapterNumber for same novel → 400/409 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
310 |  |  | TC-BE-22-009 | DRAFT → PUBLISHED: novels.totalChapters incremented by 1 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
311 |  |  | TC-BE-22-010 | PUBLISHED → DRAFT: novels.totalChapters decremented by 1 | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
312 |  |  | TC-BE-22-011 | DRAFT → PUBLISHED: Meilisearch indexChapter() called | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
313 |  |  | TC-BE-22-012 | DRAFT → PUBLISHED: fanOutNewChapterNotification() called for followers | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
314 |  |  | TC-BE-22-013 | Meilisearch indexing failure does NOT roll back the chapter DB commit | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
315 |  |  | TC-BE-22-014 | Notification failure does NOT roll back the chapter DB commit | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
316 |  |  | TC-BE-22-015 | isVip=true, coinCost omitted → coinCost defaults to 1 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
317 |  |  | TC-BE-22-016 | isVip=false → coinCost set to null regardless of input | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
318 |  |  | TC-BE-22-017 | wordCount recalculated on content update (content.trim().split(/s+/).length) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
319 |  |  | TC-BE-22-018 | Chapter delete for PUBLISHED chapter → totalChapters decremented | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
320 |  |  | TC-BE-22-019 | Cache invalidated after chapter update (chapter:novelId:chapterNumber key) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
321 | UC-23 | Admin Manage System | TC-BE-23-001 | /api/admin/* → 401 for unauthenticated | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
322 |  |  | TC-BE-23-002 | /api/admin/* → 403 for reader role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
323 |  |  | TC-BE-23-003 | /api/admin/* → 403 for curator role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
324 |  |  | TC-BE-23-004 | /api/admin/* → 200 for admin role | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
325 |  |  | TC-BE-23-005 | User suspension: users.status=SUSPENDED + audit_logs row in same transaction | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
326 |  |  | TC-BE-23-006 | User suspension: if transaction fails, neither status nor log is written | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
327 |  |  | TC-BE-23-007 | Role change: users.role updated + audit_logs row in same transaction | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
328 |  |  | TC-BE-23-008 | Report resolution: reports.status updated + audit_logs row in same transaction | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
329 |  |  | TC-BE-23-009 | Content hide: novel/chapter hidden + audit_logs row in same transaction | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
330 |  |  | TC-BE-23-010 | 100% of admin mutations produce a corresponding audit_logs entry | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
331 |  |  | TC-BE-23-011 | audit_logs row includes adminId, action, targetType, targetId, timestamp | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
332 |  |  | TC-BE-23-012 | Suspended user: sign-in attempt rejected (session not created) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
333 |  |  | TC-BE-23-013 | Hidden novel: de-indexed from Meilisearch on hide action | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
334 |  |  | TC-BE-23-014 | Coin package create → audit_logs entry written | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
335 |  |  | TC-BE-23-015 | Coin package deactivate → audit_logs entry written | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
336 |  |  | TC-BE-23-016 | Audit log list endpoint returns entries in reverse-chronological order | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
337 |  |  | TC-BE-23-017 | Admin cannot perform actions on own account via admin panel | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
338 | NFR | Non-Functional / System Quality | TC-BE-NFR-001 | GET /api/health → 200 JSON with status, timestamp, and per-dependency check results | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
339 |  |  | TC-BE-NFR-002 | GET /api/health: database check returns latencyMs; status=ok when DB reachable | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
340 |  |  | TC-BE-NFR-003 | GET /api/health: overall status=degraded when Redis unreachable but DB healthy | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
341 |  |  | TC-BE-NFR-004 | GET /api/health: overall status=down (HTTP 503) when DB unreachable | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
342 |  |  | TC-BE-NFR-005 | GET /api/health: check results include latencyMs for each dependency | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
343 |  |  | TC-BE-NFR-006 | Login rate limiter: 10 attempts/15 min per IP (Upstash Redis sliding window) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
344 |  |  | TC-BE-NFR-007 | Serverless cold-start completes < 500 ms (Drizzle ORM bundle size target) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
345 |  |  | TC-BE-NFR-008 | Neon HTTP driver used (not TCP): no persistent connection pool warnings | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
346 |  |  | TC-BE-NFR-009 | All DB writes involving coinBalance use db.transaction() — enforced by code | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
347 |  |  | TC-BE-NFR-010 | Module boundary: src/modules/ do not import from sibling modules | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
348 |  |  | TC-BE-NFR-011 | Module boundary: src/app/ pages do not import from src/db/schema/ directly | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
349 |  |  | TC-BE-NFR-012 | Structured logger (pino) emits JSON to stdout on every error/warn event | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
350 |  |  | TC-BE-NFR-013 | Meilisearch fallback logs WARN with query and error context | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
351 |  |  | TC-BE-NFR-014 | Redis cache failure logs WARN; DB fallback executes transparently | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
352 |  |  | TC-BE-NFR-015 | MoMo webhook error logs ERROR with orderId and transId context | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
353 |  |  | TC-BE-NFR-016 | Notification fan-out failure logs ERROR with novelId and chapterId | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
354 |  |  | TC-BE-NFR-017 | OpenTelemetry traces registered via @vercel/otel on startup | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
355 |  |  | TC-BE-NFR-018 | Web vitals (LCP, CLS, INP, TTFB) sent to POST /api/vitals in production | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
356 |  |  | TC-BE-NFR-019 | XSS: all chapter content sanitized server-side with DOMPurify before storage | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
357 |  |  | TC-BE-NFR-020 | All API routes return Content-Type: application/json (no mixed types) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
358 |  |  | TC-BE-NFR-021 | HTTP Strict-Transport-Security header present on all production HTTPS responses | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
359 |  |  | TC-BE-NFR-022 | X-Content-Type-Options: nosniff header present on all API responses | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
360 |  |  | TC-BE-NFR-023 | X-Frame-Options: DENY header present on HTML page responses | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
361 |  |  | TC-BE-NFR-024 | SQL injection in ?q= search param → safe; no 500; empty result or ignored | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
362 |  |  | TC-BE-NFR-025 | SQL injection in novel slug URL param → 404; no 500 or data leak | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
363 |  |  | TC-BE-NFR-026 | CORS: /api/* rejects requests from non-whitelisted origins (no ACAO wildcard) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
364 |  |  | TC-BE-NFR-027 | coin_transactions SUM(amount) per user always equals users.coinBalance (invariant) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
365 |  |  | TC-BE-NFR-028 | All datetime columns stored as UTC; client formats to ICT (UTC+7) for display | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
366 |  |  | TC-BE-NFR-029 | Concurrent rate-limit increments for same IP use Redis INCR atomic; counter never drifts | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
367 |  |  | TC-BE-NFR-030 | POST /api/vitals receives web-vital payload; returns 204; metric logged via pino | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
| Req ID | Req Desc | Test Cases
| UC-01 | Register Account | 20
| UC-02 | Sign In with Email | 14
| UC-03 | Sign In with Google | 10
| UC-04 | Sign Out | 6
| UC-05 | Reset Password | 14
| UC-06 | Browse Novel List | 22
| UC-07 | Search Novels | 18
| UC-08 | Filter Novels | 12
| UC-09 | View Novel Detail | 20
| UC-10 | Read Chapter | 21
| UC-11 | Adjust Reader Settings | 11
| UC-12 | Follow Novel | 8
| UC-13 | Track Reading Progress | 8
| UC-14 | View Library | 8
| UC-15 | Write Review | 17
| UC-16 | Leave Comment | 18
| UC-17 | Purchase Coins via MoMo | 22
| UC-18 | Unlock VIP Chapter | 20
| UC-19 | Update Profile | 8
| UC-20 | Change Password | 10
| UC-21 | Curator Manage Novel | 14
| UC-22 | Curator Manage Chapter | 19
| UC-23 | Admin Manage System | 17
| NFR | Non-Functional / System Quality | 30
| TOTAL |  | 367

## UI AND INTEGRATION TESTING
No | Req ID | Req Desc | TC ID | TC Desc | Test Design | Test Designer | UAT Test Req? | Test Execution |  |  | Defects? | Defect ID | Defect Status | Req Coverage Status
[8 empty] | Test Env | UAT Env | Prod Env
1 | UC-01/02 | Registration & Sign-in Flows | TC-UI-AUTH-001 | Sign-up form shows inline error for empty name on submit | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Partial
2 |  |  | TC-UI-AUTH-002 | Sign-up form shows inline error for invalid email format | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
3 |  |  | TC-UI-AUTH-003 | Sign-up form shows inline error for password < 8 chars | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
4 |  |  | TC-UI-AUTH-004 | Successful sign-up → user redirected to /; navbar shows user avatar | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
5 |  |  | TC-UI-AUTH-005 | Navbar shows coin balance = 0 immediately after registration | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
6 |  |  | TC-UI-AUTH-006 | Sign-in with correct credentials → dashboard loads, user name visible in navbar | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
7 |  |  | TC-UI-AUTH-007 | Sign-in with wrong password → error message on page; no redirect | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
8 |  |  | TC-UI-AUTH-008 | 10+ failed sign-ins → rate-limit error message displayed on form | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
9 |  |  | TC-UI-AUTH-009 | Sign-in page: "Tiếp tục với Google" button present and clickable | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
10 |  |  | TC-UI-AUTH-010 | Sign-up page: "Tiếp tục với Google" button present and clickable | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
11 |  |  | TC-UI-AUTH-011 | Sign-out via user dropdown → navbar reverts to "Đăng nhập" / "Đăng ký" | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
12 |  |  | TC-UI-AUTH-012 | After sign-out, navigating to /library → redirected to /sign-in?callbackUrl | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
13 |  |  | TC-UI-AUTH-024 | Sign-in form: password field uses type=password; plaintext not visible | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
14 |  |  | TC-UI-AUTH-025 | Session persists across new tabs opened in same browser (shared origin cookie) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
15 |  |  | TC-UI-AUTH-026 | Registration: submit button disabled while request is in-flight (no double submit) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
16 | UC-05 | Reset Password Flow | TC-UI-AUTH-013 | "Quên mật khẩu?" link on /sign-in navigates to forgot-password form | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Partial
17 |  |  | TC-UI-AUTH-014 | Submitting any email (found or not) shows neutral confirmation message | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
18 |  |  | TC-UI-AUTH-015 | Valid reset link opens new-password form with two fields | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
19 |  |  | TC-UI-AUTH-016 | New password < 8 chars: inline error shown; form not submitted | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
20 |  |  | TC-UI-AUTH-017 | Successful password reset → redirected to /sign-in with success message | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
21 |  |  | TC-UI-AUTH-018 | Expired or already-used reset link → error page with "Gửi lại" option | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
22 | UC-02 | Protected Route Redirects | TC-UI-AUTH-019 | Unauthenticated guest visits /library → redirected to /sign-in?callbackUrl=/library | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Partial
23 |  |  | TC-UI-AUTH-020 | Unauthenticated guest visits /settings → redirected to /sign-in | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
24 |  |  | TC-UI-AUTH-021 | After sign-in from redirect, callbackUrl honored → lands on /library | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
25 |  |  | TC-UI-AUTH-022 | Authenticated reader cannot access /admin → 403 page shown | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
26 |  |  | TC-UI-AUTH-023 | Authenticated curator cannot access /admin → 403 page shown | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
27 | UC-06 | Browse & Filter Novel List | TC-UI-BROWSE-001 | /novels page renders correctly with JavaScript disabled (SSR check) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
28 |  |  | TC-UI-BROWSE-002 | Novel grid shows cover image, title, status badge, chapter count | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
29 |  |  | TC-UI-BROWSE-003 | "Hoàn thành" status pill click → URL gains ?status=COMPLETED; list re-renders | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
30 |  |  | TC-UI-BROWSE-004 | Clicking same active status pill deselects it; list reverts to unfiltered | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
31 |  |  | TC-UI-BROWSE-005 | Genre pill selection adds ?genre= to URL and filters list | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
32 |  |  | TC-UI-BROWSE-006 | Both status and genre pills active → AND-filtered results displayed | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
33 |  |  | TC-UI-BROWSE-007 | Filter URL shared with another user → identical view on load | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
34 |  |  | TC-UI-BROWSE-008 | Zero-match filter → "Không tìm thấy truyện" empty state visible | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
35 |  |  | TC-UI-BROWSE-009 | Pagination control: page 2 link loads next set of novels | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
36 |  |  | TC-UI-BROWSE-010 | Mobile viewport (375px): novel grid renders as 1-column; no horizontal scroll | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
37 |  |  | TC-UI-BROWSE-011 | Novel card click navigates to correct /novels/[slug] URL | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
38 |  |  | TC-UI-BROWSE-012 | Sort selector change re-fetches with new ?sort= param; list updates without full reload | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
39 | UC-07 | Search Novels | TC-UI-SEARCH-001 | Typing in search input updates ?q= param after ~300 ms debounce | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
40 |  |  | TC-UI-SEARCH-002 | Typo query returns related novels (Meilisearch typo tolerance) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
41 |  |  | TC-UI-SEARCH-003 | Clearing search input removes ?q= and restores unfiltered list | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
42 |  |  | TC-UI-SEARCH-004 | Search + status filter active simultaneously: both applied in results | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
43 |  |  | TC-UI-SEARCH-005 | Search result count updates to reflect matched novels | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
44 |  |  | TC-UI-SEARCH-006 | Search debounce: rapid typing fires only one API request per 300 ms window | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
45 |  |  | TC-UI-SEARCH-007 | No results found: "Không tìm thấy truyện nào" empty state shown | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
46 |  |  | TC-UI-SEARCH-008 | Vietnamese diacritics typed in search box return accented matches correctly | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
47 | UC-09 | Novel Detail Page | TC-UI-NOVEL-001 | Novel detail <head> contains og:title (view-source check) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
48 |  |  | TC-UI-NOVEL-002 | Novel detail <head> contains og:description | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
49 |  |  | TC-UI-NOVEL-003 | Cover image loaded from res.cloudinary.com (network tab) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
50 |  |  | TC-UI-NOVEL-004 | Navigating to /novels/non-existent-slug shows 404 page | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
51 |  |  | TC-UI-NOVEL-005 | VIP chapters show amber lock icon in chapter list | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
52 |  |  | TC-UI-NOVEL-006 | No reading progress → "Đọc từ đầu" CTA links to chapter 1 | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
53 |  |  | TC-UI-NOVEL-007 | With reading progress → "Tiếp tục đọc chương N" CTA correct | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
54 |  |  | TC-UI-NOVEL-008 | Novel with no reviews → reviews section shows "Chưa có đánh giá" | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
55 |  |  | TC-UI-NOVEL-009 | Recommendations grid shows same-genre novels | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
56 |  |  | TC-UI-NOVEL-010 | Novel cover image uses loading="lazy"; does not block page render | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
57 |  |  | TC-UI-NOVEL-011 | Chapter list sorted ascending by chapterNumber by default | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
58 |  |  | TC-UI-NOVEL-012 | Novel status badge color matches status (green=ONGOING, blue=COMPLETED, etc.) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
59 |  |  | TC-UI-NOVEL-013 | Genre tag pills on novel detail link to /novels?genre=X filtered list | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
60 | UC-10 | Read Chapter | TC-UI-READ-001 | Free chapter: full text visible for unauthenticated guest | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
61 |  |  | TC-UI-READ-002 | VIP chapter: lock overlay shown for guest; chapter text absent from DOM (Inspect) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
62 |  |  | TC-UI-READ-003 | VIP chapter: "Đăng nhập để đọc" link shown for unauthenticated user | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
63 |  |  | TC-UI-READ-004 | VIP chapter: coin-purchase prompt shown for authenticated reader with 0 coins | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
64 |  |  | TC-UI-READ-005 | After clicking "Mở khóa", chapter content revealed; coin balance in navbar decrements | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
65 |  |  | TC-UI-READ-006 | Prev chapter button absent on chapter 1 (no prev) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
66 |  |  | TC-UI-READ-007 | Next chapter button absent on last chapter | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
67 |  |  | TC-UI-READ-008 | Chapter nav works: clicking Next loads next chapter correctly | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
68 |  |  | TC-UI-READ-009 | Reading time estimate displayed in reader top bar ("~N phút đọc") | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
69 |  |  | TC-UI-READ-014 | Breadcrumb on chapter page links back to correct novel detail | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
70 |  |  | TC-UI-READ-015 | Chapter text is selectable (user-select not overridden to none) | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
71 |  |  | TC-UI-READ-016 | Long chapter content does not cause horizontal overflow or layout shift | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
72 |  |  | TC-UI-READ-017 | Reader renders correctly on mobile viewport (375px); text is readable | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
73 | UC-11 | Reader Settings | TC-UI-READ-010 | Font size change applied immediately to chapter text | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
74 |  |  | TC-UI-READ-011 | Dark theme persists across browser reload without flash | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
75 |  |  | TC-UI-READ-012 | Settings panel opens on gear icon click; closes on outside click | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
76 |  |  | TC-UI-READ-013 | Settings do not affect site navigation or global theme | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
77 | UC-12/13/14 | Library, Follow & Progress | TC-UI-LIB-001 | "Theo dõi" button toggles to "Đang theo dõi" for authenticated user | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
78 |  |  | TC-UI-LIB-002 | "Theo dõi" button shows sign-in prompt for unauthenticated guest | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
79 |  |  | TC-UI-LIB-003 | Followed novel appears in /library list | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
80 |  |  | TC-UI-LIB-004 | Unfollowing novel removes it from /library list | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
81 |  |  | TC-UI-LIB-005 | After reading chapter N, novel detail shows "Tiếp tục đọc chương N" | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
82 |  |  | TC-UI-LIB-006 | Progress bar shown in library card; percentage matches chapter progress | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
83 |  |  | TC-UI-LIB-007 | Library tab "Đang đọc" shows only in-progress novels | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
84 |  |  | TC-UI-LIB-008 | Library tab "Hoàn thành" shows only completed novels | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
85 |  |  | TC-UI-LIB-009 | Notification bell shows unread count badge when notifications exist | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
86 |  |  | TC-UI-LIB-010 | Library page: unauthenticated guest immediately redirected to /sign-in | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
87 |  |  | TC-UI-LIB-011 | Empty library state shows illustration + "Khám phá truyện" CTA link to /novels | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
88 |  |  | TC-UI-LIB-012 | Library card shows last-read chapter number and progress percentage | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
89 | UC-17/18 | Payments & Coin Unlock | TC-UI-PAY-001 | /pricing lists all active coin packages with VND price and coin amount | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
90 |  |  | TC-UI-PAY-002 | Clicking "Mua" on a package → redirected to MoMo payment page (external URL) | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
91 |  |  | TC-UI-PAY-003 | Coin balance shown in navbar for authenticated user | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
92 |  |  | TC-UI-PAY-004 | After successful payment return, coin balance in navbar updated | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
93 |  |  | TC-UI-PAY-005 | Cancelled/failed MoMo return → /pricing with error notice | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
94 |  |  | TC-UI-PAY-006 | VIP chapter page shows coin cost and "Mở khóa" button | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
95 |  |  | TC-UI-PAY-007 | Zero-balance: "Mở khóa" shows "Mua xu" shortcut link instead | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
96 |  |  | TC-UI-PAY-008 | Unlock confirmation dialog shows coin cost and current balance | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
97 |  |  | TC-UI-PAY-009 | After unlock, "Mở khóa" button replaced by chapter content (no reload needed) | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
98 |  |  | TC-UI-PAY-010 | Transaction history page lists past coin purchases in reverse-chronological order | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
99 |  |  | TC-UI-PAY-011 | Coin package with bonus shows "+N bonus xu" label on /pricing page | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
100 |  |  | TC-UI-PAY-012 | Redirect button to MoMo disabled while payment is initiating (no double-submit) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
101 |  |  | TC-UI-PAY-013 | Insufficient-coin state: "Mở khóa" shows coin requirement and balance shortfall | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
102 | UC-15/16 | Reviews & Comments | TC-UI-COMM-001 | Review form on novel detail visible for authenticated reader | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
103 |  |  | TC-UI-COMM-002 | Star rating UI: clicking star 4 selects 4; reclick deselects | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
104 |  |  | TC-UI-COMM-003 | Rating required: submitting without star → inline error shown | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
105 |  |  | TC-UI-COMM-004 | Review body > 2000 chars: character counter turns red; submit blocked | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
106 |  |  | TC-UI-COMM-005 | Comment text box on novel detail visible for authenticated reader | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
107 |  |  | TC-UI-COMM-006 | Unauthenticated user: comment area shows "Đăng nhập để bình luận" | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
108 |  |  | TC-UI-COMM-007 | Reply button on comment opens indented reply input | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
109 |  |  | TC-UI-COMM-008 | New comment appears at top of list immediately after submit | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
110 | UC-19/20 | Profile & Password | TC-UI-PROF-001 | /settings page accessible for authenticated user | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Partial
111 |  |  | TC-UI-PROF-002 | Display name update: save shows success toast; new name in navbar | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
112 |  |  | TC-UI-PROF-003 | Change password form hidden for Google-only accounts | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
113 |  |  | TC-UI-PROF-004 | Wrong current password on change-password form → error shown | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
114 |  |  | TC-UI-PROF-005 | Password change success → success toast; user stays signed in | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
115 | UC-21/22 | Curator CMS | TC-UI-CUR-001 | "CMS" nav link visible only for CURATOR and ADMIN roles | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
116 |  |  | TC-UI-CUR-002 | /curator accessible for curator role; /curator blocked (403) for reader | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
117 |  |  | TC-UI-CUR-003 | Novel creation form: submitting empty title → validation error inline | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
118 |  |  | TC-UI-CUR-004 | Slug field auto-populated from title; can be manually edited | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
119 |  |  | TC-UI-CUR-005 | Cover image upload widget shows preview after Cloudinary upload | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
120 |  |  | TC-UI-CUR-006 | New chapter created as DRAFT → not visible in public chapter list | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
121 |  |  | TC-UI-CUR-007 | DRAFT chapter published via CMS → appears in public chapter list | Complete | NovelHub QA | Yes | Not Run | Not Run | Not Run |  |  |  | Not Covered
122 |  |  | TC-UI-CUR-008 | Chapter list in CMS shows DRAFT chapters that guests cannot see | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
123 |  |  | TC-UI-CUR-009 | XSS attempt in chapter content field: <script> removed in preview render | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
124 |  |  | TC-UI-CUR-010 | Chapter editor displays live word count; updates as content is typed | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
125 |  |  | TC-UI-CUR-011 | Novel status change to COMPLETED: confirmation dialog shown before submission | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
126 |  |  | TC-UI-CUR-012 | DRAFT badge shown on chapter cards in CMS that are not yet published | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
127 | UC-23 | Admin Panel | TC-UI-ADM-001 | /admin accessible with ADMIN role; reader sees 403 error page | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
128 |  |  | TC-UI-ADM-002 | User list shows all users with role, status, and coin balance | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
129 |  |  | TC-UI-ADM-003 | Suspending a user from admin panel → status changes; user cannot sign in | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
130 |  |  | TC-UI-ADM-004 | Audit log table shows action, adminId, targetId, timestamp | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
131 |  |  | TC-UI-ADM-005 | Coin package management: create new package → appears in /pricing | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
132 |  |  | TC-UI-ADM-006 | Report queue shows pending reports; resolution removes from queue | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
133 |  |  | TC-UI-ADM-007 | Unsuspending a user restores sign-in access; status badge changes to active | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
134 |  |  | TC-UI-ADM-008 | Role promotion reader→curator: reflected in navbar and route access on next session | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
135 | NFR | Error Boundaries & Observability | TC-UI-OBS-001 | error.tsx: route error shows Vietnamese error message + "Thử lại" button | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
136 |  |  | TC-UI-OBS-002 | "Thử lại" button in error.tsx calls reset() and reloads route segment | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
137 |  |  | TC-UI-OBS-003 | global-error.tsx: catastrophic error shows "Tải lại" button (minimal HTML) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
138 |  |  | TC-UI-OBS-004 | error.tsx shows error.digest ID for traceable support reference | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
139 |  |  | TC-UI-OBS-005 | GET /api/health returns 200 JSON with status and check results | Complete | NovelHub QA | Yes | Passed | Not Run | Not Run |  |  |  | Covered
140 |  |  | TC-UI-OBS-006 | Web vitals POST fires to /api/vitals on page load (confirmed via network tab) | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
141 |  |  | TC-UI-OBS-007 | error.tsx: digest ID shown is short alphanumeric code, not full stack trace | Complete | NovelHub QA | No | Not Run | Not Run | Not Run |  |  |  | Not Covered
142 |  |  | TC-UI-OBS-008 | All unknown routes (/foo/bar) render the 404 not-found page, not a 500 | Complete | NovelHub QA | No | Passed | Not Run | Not Run |  |  |  | Covered
| Req ID | Req Desc | Test Cases
| UC-01/02 | Registration & Sign-in Flows | 15
| UC-05 | Reset Password Flow | 6
| UC-02 | Protected Route Redirects | 5
| UC-06 | Browse & Filter Novel List | 12
| UC-07 | Search Novels | 8
| UC-09 | Novel Detail Page | 13
| UC-10 | Read Chapter | 13
| UC-11 | Reader Settings | 4
| UC-12/13/14 | Library, Follow & Progress | 12
| UC-17/18 | Payments & Coin Unlock | 13
| UC-15/16 | Reviews & Comments | 8
| UC-19/20 | Profile & Password | 5
| UC-21/22 | Curator CMS | 12
| UC-23 | Admin Panel | 8
| NFR | Error Boundaries & Observability | 8
| TOTAL |  | 142